## Module Requirements
Module | Owner Type | Phase | Requirement | Priority Notes
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | User signup/login | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Role selection: Client, Advocate, Admin | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Basic session management | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Basic profile creation | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Redirect users based on role | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Logout functionality | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Store user role in database | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | GREEN - Prototype / Build Now | Protect dashboard routes based on role | Investor-convincing feature
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Phone OTP login | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | OAuth login with Google | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Password reset | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Email verification | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Multi-factor authentication | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Account deletion request | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Device/session management | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Login activity history | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | Suspicious login detection | Build after mentors/investors/validation
Module 1: Authentication & User Identity | Frontend + Backend/Supabase developer | RED - Later / Full Platform | DPDP-compliant consent management | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Client welcome dashboard | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Display saved/recommended advocates | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Show consultation requests | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Show recent messages | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | AI legal assistant shortcut | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Basic uploaded document placeholder | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Polished empty states | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | GREEN - Prototype / Build Now | Navigation to directory, AI assistant, messages, profile | Investor-convincing feature
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Payment history | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Consultation history | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Case timeline | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Legal document vault | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Saved legal topics | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | AI conversation history | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Court date reminders | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Refund/dispute requests | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Downloadable invoices | Build after mentors/investors/validation
Module 2: Client Dashboard | Frontend developer | RED - Later / Full Platform | Multi-language dashboard | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Advocate listing page | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Advocate cards with name, practice area, location, experience, languages, fee, verification badge, rating | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Search by name/practice area | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Filters: practice area, city, experience, language | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | View Profile button | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Request Consultation button | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | GREEN - Prototype / Build Now | Seed demo advocate data | Investor-convincing feature
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Advanced ranking algorithm | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Availability-based filtering | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Real ratings/reviews | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Fee range filter | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Sponsored visibility after legal review | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Geo-location discovery | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Verified-only toggle | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Response-time sorting | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Recommendation engine | Build after mentors/investors/validation
Module 3: Advocate Directory / Marketplace | Frontend + Backend developer | RED - Later / Full Platform | Abuse/fake profile detection | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Full advocate profile page | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Show name, photo/avatar, bio, practice areas, Bar Council number, experience, languages, city/state, fee, verification badge, availability | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Request consultation CTA | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Message advocate CTA | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Mock reviews/testimonials | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | GREEN - Prototype / Build Now | Professional trust-focused layout | Investor-convincing feature
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Real verified reviews | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Document/certification display | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Calendar availability | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Conflict-of-interest notice | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Response rate | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Consultation success metrics | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Profile analytics | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Report profile button | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Verification history | Build after mentors/investors/validation
Module 4: Advocate Profile Page | Frontend developer | RED - Later / Full Platform | Public/private profile controls | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Consultation request form | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Fields: legal category, description, mode, preferred date/time, city/state, urgency | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Save request to database | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Show request in client dashboard | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Show request in advocate dashboard | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Statuses: Pending, Accepted, Rejected, Completed | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | GREEN - Prototype / Build Now | Confirmation toast/message | Investor-convincing feature
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Real slot booking calendar | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Availability management | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Rescheduling | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Cancellation policy | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Payment before booking | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Refund workflow | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Email/SMS reminders | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Google Calendar sync | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | Razorpay integration | Build after mentors/investors/validation
Module 5: Consultation Request / Booking | Full-stack developer | RED - Later / Full Platform | No-show handling | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Basic inbox page | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Client-advocate conversation view | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Send/receive messages using Supabase | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Message history | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Conversation list | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Simple timestamps | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Admin warning message support | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | GREEN - Prototype / Build Now | Basic role-based message visibility | Investor-convincing feature
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Real-time chat | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Typing indicators | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Read receipts | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | File sharing | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Document previews | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Push notifications | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Message search | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Conversation categories | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Encrypted file storage | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Malware scanning | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Audit logs | Build after mentors/investors/validation
Module 6: Secure Messaging / Inbox | Full-stack developer | RED - Later / Full Platform | Message retention policy | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | AI legal Q&A page | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Ask legal questions | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Simple-language AI responses | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Strong disclaimer: general legal information, not legal advice | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Suggested topics: tenant, family, consumer, employment, property, criminal basics | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Talk to an advocate CTA | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Save basic query history | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | GREEN - Prototype / Build Now | Prompt guardrails against definitive legal advice | Investor-convincing feature
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Backend-secured OpenAI API integration | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Retrieval-based legal knowledge base | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Indian law citations | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | State-specific guidance | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Multi-language AI: English/Hindi/Marathi | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Legal document summarization | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | AI answer audit logs | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Hallucination detection | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Urgent situation escalation | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | AI-based advocate recommendation | Build after mentors/investors/validation
Module 7: AI Legal Learning Assistant | AI/frontend developer | RED - Later / Full Platform | Human-reviewed FAQs | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Advocate dashboard homepage | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Profile completion | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Verification status | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Consultation requests | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Recent messages | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Basic stats: views, leads, completed consultations | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Accept/reject request | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Edit basic profile | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | GREEN - Prototype / Build Now | Set simple availability text | Investor-convincing feature
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Full lead pipeline | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Appointment calendar | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Earnings dashboard | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Payout tracking | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Client notes | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Intake responses | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Availability slots | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Auto-replies | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Review management | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Profile analytics | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Document request templates | Build after mentors/investors/validation
Module 8: Advocate Dashboard | Frontend + Backend developer | RED - Later / Full Platform | Subscription plan management | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Admin dashboard page | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | View all users | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Filter users by role | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Search users | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | View pending advocate verification | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Approve/reject verification | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Send warning to user | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Edit user role/name | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Basic stats: users, advocates, pending verifications, requests | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | GREEN - Prototype / Build Now | Trust/control-center UI | Investor-convincing feature
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Document verification workflow | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Advocate suspension | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Dispute management | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Refund management | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Abuse reports | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Review moderation | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | AI answer audit | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Admin activity logs | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Role-based admin permissions | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Analytics dashboard | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Compliance dashboard | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Data deletion/export requests | Build after mentors/investors/validation
Module 9: Admin Dashboard / Trust & Verification | Full-stack developer | RED - Later / Full Platform | Legal escalation workflows | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | GREEN - Prototype / Build Now | Advocate submits Bar Council number, practice areas, experience, location, languages | Investor-convincing feature
Module 10: Advocate Verification System | Backend/Supabase developer | GREEN - Prototype / Build Now | Store verification status | Investor-convincing feature
Module 10: Advocate Verification System | Backend/Supabase developer | GREEN - Prototype / Build Now | Admin can mark Pending, Verified, Rejected | Investor-convincing feature
Module 10: Advocate Verification System | Backend/Supabase developer | GREEN - Prototype / Build Now | Show verification badge on directory/profile | Investor-convincing feature
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Document upload | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Bar Council ID upload | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Certificate of Practice upload | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Manual document review | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Annual re-verification | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Suspended/debarred tracking | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Verification notes | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Rejection reason | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | Verification audit history | Build after mentors/investors/validation
Module 10: Advocate Verification System | Backend/Supabase developer | RED - Later / Full Platform | External verification partnerships | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Core tables: profiles, advocates, consultation_requests, messages, ai_queries, reviews, admin_actions | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Supabase Auth | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Basic Row Level Security | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Role field | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Seed demo users/advocates | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Public read access for verified advocate profiles | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | GREEN - Prototype / Build Now | Private access for messages/requests | Investor-convincing feature
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Strict RLS policies | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Audit logs | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Storage buckets for documents | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Signed URLs | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Data retention rules | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Data deletion/export flows | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Backups | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Payment tables | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Dispute tables | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Notification tables | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Analytics events | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Consent records | Build after mentors/investors/validation
Module 11: Database & Supabase Backend | Backend/Supabase developer | RED - Later / Full Platform | Security monitoring | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | GREEN - Prototype / Build Now | Mock payment UI | Investor-convincing feature
Module 12: Payments & Monetization | Backend/payment developer | GREEN - Prototype / Build Now | Consultation fee displayed | Investor-convincing feature
Module 12: Payments & Monetization | Backend/payment developer | GREEN - Prototype / Build Now | Payment coming soon flow | Investor-convincing feature
Module 12: Payments & Monetization | Backend/payment developer | GREEN - Prototype / Build Now | Fake statuses: Pending, Paid, Refunded | Investor-convincing feature
Module 12: Payments & Monetization | Backend/payment developer | GREEN - Prototype / Build Now | Pricing idea section for pitch/demo | Investor-convincing feature
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Razorpay integration | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Payment gateway webhooks | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Advocate payouts | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Platform commission | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Refunds | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Cancellation fees | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | GST/invoice handling | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Payment dispute handling | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Subscription plans for advocates | Build after mentors/investors/validation
Module 12: Payments & Monetization | Backend/payment developer | RED - Later / Full Platform | Financial reconciliation dashboard | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | GREEN - Prototype / Build Now | Display mock reviews | Investor-convincing feature
Module 13: Reviews & Ratings | Frontend + Backend developer | GREEN - Prototype / Build Now | Show rating count | Investor-convincing feature
Module 13: Reviews & Ratings | Frontend + Backend developer | GREEN - Prototype / Build Now | Basic review form after completed consultation | Investor-convincing feature
Module 13: Reviews & Ratings | Frontend + Backend developer | GREEN - Prototype / Build Now | Store review in database | Investor-convincing feature
Module 13: Reviews & Ratings | Frontend + Backend developer | GREEN - Prototype / Build Now | Link reviews to advocate | Investor-convincing feature
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Verified consultation-only reviews | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Review moderation | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Report review | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Advocate reply | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Prevent confidential case details | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Fake review detection | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Review dispute workflow | Build after mentors/investors/validation
Module 13: Reviews & Ratings | Frontend + Backend developer | RED - Later / Full Platform | Rating breakdown: clarity, professionalism, responsiveness, punctuality | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | GREEN - Prototype / Build Now | Placeholder document section | Investor-convincing feature
Module 14: Documents & File Management | Backend + Frontend developer | GREEN - Prototype / Build Now | Optional basic upload for demo | Investor-convincing feature
Module 14: Documents & File Management | Backend + Frontend developer | GREEN - Prototype / Build Now | Uploaded document list | Investor-convincing feature
Module 14: Documents & File Management | Backend + Frontend developer | GREEN - Prototype / Build Now | Attach document to consultation request | Investor-convincing feature
Module 14: Documents & File Management | Backend + Frontend developer | GREEN - Prototype / Build Now | File metadata: name, type, uploaded date | Investor-convincing feature
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Secure Supabase Storage | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Private buckets | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Signed download URLs | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | File access permissions | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Malware scanning | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Document expiry | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Document sharing controls | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | AI document summary | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Legal document templates | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Encryption strategy | Build after mentors/investors/validation
Module 14: Documents & File Management | Backend + Frontend developer | RED - Later / Full Platform | Retention/deletion policy | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | GREEN - Prototype / Build Now | In-app toast notifications | Investor-convincing feature
Module 15: Notifications | Backend/full-stack developer | GREEN - Prototype / Build Now | Dashboard notification cards | Investor-convincing feature
Module 15: Notifications | Backend/full-stack developer | GREEN - Prototype / Build Now | Notify on request submitted, accepted/rejected, message received, verification approved/rejected | Investor-convincing feature
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Email notifications | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | SMS notifications | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | WhatsApp notifications | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Push notifications | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Reminder system | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Notification preferences | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Calendar reminders | Build after mentors/investors/validation
Module 15: Notifications | Backend/full-stack developer | RED - Later / Full Platform | Notification audit logs | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | Professional landing page | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | Value proposition: verified advocates, AI legal help, consultations, secure communication | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | CTAs: Find Advocate, Ask AI, Join as Advocate | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | Trust sections | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | Demo-friendly flow | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | GREEN - Prototype / Build Now | Mobile responsive UI | Investor-convincing feature
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | SEO pages for legal topics | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | City/practice-area landing pages | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Blog/legal awareness content | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Advocate acquisition pages | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Partnership pages | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Testimonials | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Press/media kit | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | Conversion analytics | Build after mentors/investors/validation
Module 16: Landing Page & Pitch Experience | Frontend/UI designer | RED - Later / Full Platform | A/B testing | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Basic terms page | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Basic privacy page | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | AI disclaimer | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Consultation disclaimer | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Advocate verification disclaimer | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Notice that NyayaSetu does not provide legal advice directly | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | GREEN - Prototype / Build Now | Safe language across UI | Investor-convincing feature
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Full legal terms | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | DPDP compliance policy | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Data processing consent | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Grievance officer details | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Refund/cancellation policy | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Advocate platform agreement | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Client agreement | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | AI usage policy | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Data breach response plan | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Bar Council advertising compliance review | Build after mentors/investors/validation
Module 17: Legal, Compliance & Trust | Founder/legal advisor/product manager | RED - Later / Full Platform | Platform liability framework | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | GREEN - Prototype / Build Now | Basic admin stats: users, advocates, consultation requests, pending verifications, AI questions | Investor-convincing feature
Module 18: Analytics & Metrics | Backend/product analytics developer | GREEN - Prototype / Build Now | Mock growth numbers for pitch dashboard | Investor-convincing feature
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | MAU tracking | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Conversion funnel | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Advocate onboarding conversion | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Consultation booking rate | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | NPS | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Retention rate | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Response time tracking | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | AI usage analytics | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Revenue dashboard | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Cohort analytics | Build after mentors/investors/validation
Module 18: Analytics & Metrics | Backend/product analytics developer | RED - Later / Full Platform | Churn tracking | Build after mentors/investors/validation

## Team Distribution
Person | Focus Area | Assigned Modules / Responsibilities
Person 1 | Auth + Role Routing | Authentication & User Identity; Route protection; Profile creation
Person 2 | Client Side Experience | Landing Page; Client Dashboard; Advocate Directory; Advocate Profile
Person 3 | Advocate Side Experience | Advocate Dashboard; Advocate Profile Edit; Consultation Requests
Person 4 | Admin & Verification | Admin Dashboard; Advocate Verification; User Management
Person 5 | AI Assistant | AI Legal Learning Assistant; Disclaimers; Suggested topics; Advocate escalation CTA
Person 6 | Backend/Supabase | Database schema; RLS policies; Messages; Consultation requests; Seed data
Person 7 | UI/Polish & Pitch Demo | Consistent design; Empty states; Mobile responsiveness; Demo flow; Pitch polish

## Build Order
Build Order | Task
1 | Authentication + role routing
2 | Database schema + demo data
3 | Landing page
4 | Advocate directory
5 | Advocate profile
6 | Consultation request flow
7 | Client dashboard
8 | Advocate dashboard
9 | Admin dashboard
10 | AI legal assistant
11 | Messaging
12 | UI polish and final demo flow

## Legend
Color / Phase | Meaning | When to Build
GREEN - Prototype / Build Now | Required for convincing prototype | Build before demo/pitch
RED - Later / Full Platform | Professional production platform features | Build after mentors, investors, or early validation
Core Demo Flow | Client asks AI question -> finds verified advocate -> sends consultation request -> advocate receives lead -> admin verifies trust layer | Use this as pitch/demo storyline